**Release and Sprint Plans**

**I am the Scrum Master (Team Number 104)**

|  |  |
| --- | --- |
| **Student Number** | **Team Member Name** |
| 09446664 | Alice Mckellar |
| 09488383 | Aarond Dino |
| 09476814 | Luke John Tran |
| 09808299 | Koh Chongshan Maxim |

Tutor: Mr Jesse St.Germain

Version: 1.0 (Draft)

Date: 20 August 2017

**Table of Contents**

[Release Plan 1](#_Toc491036860)

[Release 1 1](#_Toc491036861)

[Logging In 1](#_Toc491036862)

[Logging Out 1](#_Toc491036863)

[Initial Search Page 1](#_Toc491036864)

[Release 2 2](#_Toc491036865)

[Student Type Features 2](#_Toc491036866)

[Tourist Type Features 2](#_Toc491036867)

[Businessman Type Features 2](#_Toc491036868)

[Administrator Type Features 2](#_Toc491036869)

[Release 3 3](#_Toc491036870)

[Feature Title 1 3](#_Toc491036871)

[Feature Title 2 3](#_Toc491036872)

[Delivery Schedule 3](#_Toc491036873)

[Estimated Velocity: 3](#_Toc491036874)

[Sprint Plan 4](#_Toc491036875)

[Sprint 1 4](#_Toc491036876)

[Current Velocity: 4](#_Toc491036877)

[Story ID: Title 4](#_Toc491036878)

[Story ID: Title 4](#_Toc491036879)

[Story ID: Title 4](#_Toc491036880)

Release Plan

# Release 1

Delivery date: XXX Total Story Points: 27

To provide the initial aspects of the websites to allow the users; Businessman, Tourists, students and administrators to log in and log out. This aspect will allow the user to create or login to the user accounts and select which region or user type they are.

## Logging In

Short paragraph summarising this feature and its business value.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 4 | Searching Page | 4 |
| ID 15 | Login Page | 4 |
| ID 21 | Create New Account | 4 |
| ID 36 | Admin Account Creation | 3 |
|  | Story Point Sub-Total: | 15 |

## Logging Out

Users will be able to log out safely and the session should be able to end once logged out. This means, once the user has terminated the browser, or, have logged out of their user account, the session should be terminated and no longer be running.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 18 | Logging Out features | 2 |
|  | Story Point Sub-Total: | 2 |

## Initial Search Page

Users should be presented, once logged in, the **BASIC** features of the account that the user has created/ selected. This allows all Users to then have a basic home page for the user classes to browse and select the information relevant to them.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 5 | Student Main Page | 2 |
| ID 16 | Tourist Main Page | 2 |
| ID 22 | Businessmen Main Page | 4 |
| ID 31 | Admin Data manipulation | 2 |
|  | Story Point Sub-Total: | 10 |

# Release 2

Delivery date: XXX Total Story Points: 46

To provide users in different categories the relevant information specific to their primary user type after logged in. Catered for three basic types of users; Student, Tourist, and Businessman. Basic users can only read given information. Whereas Administrator, a special type of user will be able to create and edit data.

## Student Type Features

Users in this category will only be able to view details of colleges, libraries and city information.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 2 | Further Education Page | 4 |
| ID 3 | Library Page | 4 |
| ID 10 | Colleges Web Links | 2 |
|  | Story Point Sub-Total: | 10 |

## Tourist Type Features

Users in this category will only be able to view details of hotels and city information.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 11 | Hotels Selection Page | 4 |
| ID 12 | Navigation Map Page (Prioritised as Should, but won’t be doing) | 3 |
| ID 13 | City Information Page | 3 |
| ID 17 | City Selection Page (Prioritised as Could, but should be done) | 2 |
|  | Story Point Sub-Total: | 12 |

## Businessman Type Features

Users in this category will only be able to view details of hotels, industries and city information.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 22 | Businessmen Information Access | 2 |
| ID 24 | Business Information / Location Access | 4 |
| ID 25 | City Information Rating Access | 3 |
| ID 28 | Locating Hotels | 4 |
|  | Story Point Sub-Total: | 13 |

## Administrator Type Features

Users in this category can create and modify all data for the city. Including uploading relevant maps to the website.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 32 | City Information Page | 2 |
| ID 33 | Information Management | 1 |
| ID 34 | Map Upload (A requirement in the project summary but prioritised as won’t, have to discuss this again) | 3 |
| ID 36 | Admin Account Creation | 3 |
| ID 37 | Other City Information | 1 |
| ID 40 | Minimalistic Admin Interface | 1 |
|  | Story Point Sub-Total: | 11 |

ID 41 > General user should be categories in which release? Administrator?

ID 42 > T&C should be on Release 1?

# Release 3

Delivery date: 2018 Total Story Points: 23

To enhance our website functionality by adding additional features on their specific homepages to improve user’s experience with new visual changes in the near future.

## Additional Features

Users can utilize these newly implemented functions specialized for their own user types.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 1 | Student Discount Page | 2 |
| ID 7 | Rating of Colleges | 3 |
| ID 9 | Events Page | 2 |
| ID 19 | Navigation System | 4 |
| ID 23 | Hotel Information Access | 3 |
| ID 26 | Account Security / History | 2 |
| ID 27 | Contacting Businesses | 1 |
|  | Story Point Sub-Total: | 17 |

## Administrator Additional Features

Administrators can better maintain and manage overall website by optimizing these new functions.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| ID 35 | Search Function | 3 |
| ID 38 | Future Updates | 2 |
| ID 39 | Admin List Viewing | 1 |
|  | Story Point Sub-Total: | 6 |

# Delivery Schedule

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 |
| Sprint 1 | | | | Sprint 2 | | | |
| Release 1 | | | | Release 2 | | | |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 14 | Week 15 |  |  |  |  |  |  |
| Sprint 3 | | | |  | |  | |
| Release 3, 4, … | | | | | | | |

## Estimated Velocity:

Sprint Plan

# Sprint 1

Total Story Points: Total Hours:

## Current Velocity:

## Story ID: Title

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  | Story Points: Total Hours: |  |  |

## Story ID: Title

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  | Story Points: Total Hours: |  |  |

## Story ID: Title

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  | Story Points: Total Hours: |  |  |