## Sheet1
Project Components | People | EWD | buffer | Total
Release 1
User Stories | 4 |  |  |  | Complete
Businessman | 1 | 1 |  |  | In progress
Students | 1 | 1 |  |  | Not started
Tourists | 1 | 1
Administrator | 1 | 1
Final User Stories | 4 | 1 | 1 + Ekka Holiday
|  |  |  | Total: 3 | Abbreviations
Sprint 1 Retrospective | 4 |  |  |  | EWD = Estimated Work Days
Team | 4 | 1 |  |  | Buffer = Holidays/ Sick Days
Individual | 1 | 1 |  |  | EWD = 1 day = 1 working hours
Acceptance List | 1 | 1 | 1
Total: 1
Logging in | 2
ID 4 (Searching Page) | 2 | 4
ID 15 (login Page) | 2 | 4
ID 21 (Create New Creation) | 2 | 4
ID 36 (Admin Account Creation) | 2 | 3 | 1
Logging out
ID 18 (Logging out Features) | 2 | 2
Initial Search Page
ID5 (Student Main Page) | 2 | 2
ID16 (Tourist Main Page) | 2 | 2
ID 22 (Businessman Page) | 2 | 2
ID 31 (Admin Data manipulation) | 2 | 2 | 1
Total: 32
Release 1
Sprint 2 Retrospective | 4
Team | 4 | 1
Individual | 1 | 1
Total: 2
Final Release | 4
Student Type Features | 2
ID 2 (Further Education Page) | 2 | 4
ID 3 (Library Page) | 2 | 4
ID 10 (College Web Links) | 2 | 3
Total: 11
Tourist Type Features | 2
ID 11 (Hotels Selection Page) | 2 | 4
ID 13 (City Information Page) | 2 | 3
ID 17 (City Selection Page) | 2 | 2
Total: 9
Businessman Type Features | 2
ID 24 (Business Information/ Location access) | 2 | 4
ID 25 (City Information Rating Access) | 2 | 3
ID 28 (Locating Hotels) | 2 | 4
Total: 11
Administrator Type Features | 2
ID 32 (City Information Page) | 2 | 2
ID 33 (Information Management) | 2 | 1
ID 34 (Map Upload) | 2 | 3
ID 37 (Other City Information) | 2 | 1
ID 40 (Minimalistic Admin Interface) | 2 | 1
Total: 8
Grand Total: 41