## Sheet1
Project Components | People | EWD | buffer | Total
Release 1
User Stories | 4 |  |  |  | Complete
Businessman | 1 | 1 |  |  | In progress
Students | 1 | 1 |  |  | Not started
Tourists | 1 | 1
Administrator | 1 | 1
Final User Stories | 4 | 1 | 1 + Ekka Holiday
|  |  |  | Total: 2 | Abbreviations
Sprint 1 Retrospective | 4 |  |  |  | EWD = Estimated Work Days
Team | 4 | 1 |  |  | Buffer = Holidays/ Sick Days
Individual | 1 | 1
Acceptance List | 1 | 1
Total: 1
Logging in
ID 4 (Searching Page) | 2
ID 15 (login Page) | 2
ID 21 (Create New Creation) | 2
ID 36 (Admin Account Creation) | 2
Logging out
ID 18 (Logging out Features) | 2
Initial Search Page
ID5 (Student Main Page) | 2
ID16 (Tourist Main Page) | 2
ID 22 (Businessman Page) | 2
ID 31 (Admin Data manipulation) | 2
Total: 32
Release 2
Sprint 2 Retrospective | 4
Team | 4 | 3
Individual | 1 | 1
Total: 4
Final Release | 4
Website Design | 2 | 5
Website Design implementations | 2 | 5
Front End coding | 2 | 5
Back End Coding | 2 | 7
Database creations/ Usage | 2 | 5 | 4
Total: 27
Overal Total: 55
Total: 11 Weeks
11/4 = 3 weeks